## WBS
Work Breakdown Structure Template
| Project Name | MediScan AI – Smart Pneumonia Diagnosis System
| Project Manager | Ahmed Gamal Abdelfatah
| Date | 2025-10-21
| Version | 1
WORK BREAKDOWN STRUCTURE
WBS Level | Task Description | Owner | Dependency | Resources Needed | Task Status | Cost | Start Date | Estimated Completion | Finish Date | Notes
1 | Initiation Phase | PMO | Approval | Project charter, sponsor support | Complete | 0 | 2025-01-10 | 2 days | 2025-03-10
1.1 | Define Scope & Goals | All team | Approval | Hardware, tools, manuals | Complete | 0 | 2025-10-03 | 3 days | 2025-06-10
1.1.1 | Non-Functional Requirements (Security, Performance) | All team | Approval | Software license, manuals | Complete | 0 | 2025-10-08 | 2 days | 2025-09-10
1.1.2 | ui database designs | Ahmed & sara | Approval | PM Assigned | Complete | 0 | 2025-09-10 | 1 day | 2025-10-10
1.1.3 | Identify Core AI Models & Datasets | Habiba & Momen | Approval | Dev team | Complete | 0 | 2025-11-10 | 2 days | 13/10/2025
2 | Planning Phase | Project Manager | Initiation deliverables | Planning tools, templates | Complete | 0 | 14/10/2025 | 3 days | 17/13/2025
2.1 | Define functional requirements | All team | Approvel | Business analysts | Complete | 0 | 2025-10-17 | 2 days | 2025-10-19
2.1.1 | User Authentication Req's | Ahmed & sara | Approvel | Login/Signup Page | Assigned | 0 | 2025-10-20 | 1 day | 2025-10-20
2.1.2 | X-ray Analysis Req's | Habiba & Momen | in progress | AI Diagnosis & Results | Complete | 0 | 2025-10-21 | 1 day | 2025-10-21
2.1.3 | Patient Records Req's | Habiba & Momen | in progress | Patient Records Management | Complete | 0 | 2025-10-22 | 1 day | 2025-10-22
2.2 | Project schedule | All team | Approvel | PM software | Complete | 0 | 23/17/2025 | 2 days | 2025-10-24
2.2.1 | Design System Architecture | Ahmed & sara | Approvel | NFRs, Tech Stack | Complete | 0 | 2025-10-25 | 1 day | 2025-10-25
2.2.2 | Backend/API Design | Ahmed & sara | Approvel | Tech Stack | In Progress | 0 | 26/10/2025 | 2 day | 2025-10-27
2.2.3 | Performance Requirements | All team | Approvel | AI Engine | In Progress | 0 | 2025-10-28 | 1 day | 2025-10-28
3 | Execution Phase | Team Leads | Planning baseline | Team, hardware | Assigned | 0 | 2025-10-29 | 10 days | 2025-07-11
3.1 | AI Engine Development & Integration | All team | in progress | Trained Models | In Progress | 0 | 2025-08-11 | 3 days | 2025-10-11
3.1.1 | Deploy CNN Models (DenseNet121, etc.) | Habiba & Momen | in progress | Trained Model | In Progress | 0 | 2025-11-11 | 1 day | 2025-11-11
3.1.2 | Presentation Layer (Frontend) Build | Ahmed & sara | in progress | UI/UX Design | Complete | 0 | 2025-12-11 | 2 day | 14/11/2025
3.2 | Build Responsive UI for Web and Mobile | Ahmed & sara | in progress | Usability Req's | Complete | 0 | 15/11/2025 | 2 day | 16/11/2025
3.2.1 | Implement X-ray Upload & Preview | Habiba & Momen | in progress | Upload Req's | Complete | 0 | 17/21/2025 | 1 day | 17/21/2025
4 | Control Phase | PMO | Execution baseline | Reports, KPIs | Assigned | 0 | 18/11/2025 | 5 days | 22/11/2025
4.1 | Quality assurance | All team | Execution | Testing scripts | Assigned | 0 | 23/11/2025 | 2 days | 25/11/2025
4.1.1 | Performance testing | All team | Deployment | Verify AI analysis time (5–10s) | Assigned | 0 | 26/11/2025 | 1 day | 26/11/2025
4.1.2 | Security testing | Ahmed & sara | System Build | Verify HTTPS/AES Encryption | Assigned | 0 | 27/11/2025 | 1 day | 27/11/2025
4.1.3 | User acceptance testing | Ahmed & sara | final build | Workstations | Assigned | 0 | 28/11/2025 | 1 day | 28/11/2025
5 | Close Phase | PMO | Project completion | Reports, sign-off | Assigned | 0 | 29/11/2025 | 3 days | 2025-01-12
5.1 | Final review | All team | Closure plan | PM team | Assigned | 0 | 2025-02-12 | 1 day | 2025-02-12
5.1.1 | Documentation | All team | Final review | Docs, templates | Assigned | 0 | 2025-03-12 | 1 day | 2025-03-12
5.1.2 | Client sign-off | All team | Documentation | Reports | Assigned | 0 | 2025-04-12 | 1 day | 2025-04-12
5.1.3 | Release resources | All team | Client sign-off | Team, assets | Assigned | 0 | 2025-05-12 | 1 day | 2025-05-12

## WBS Tree
WBS TREE Diagram
Initiation
Project Title
Project Proposal & Planning
Define objectives and scope
Subtask
Subtask
Planning
Task
Task
Subtask
Subtask
Subtask
Subtask
Subtask
Subtask
Execution
Task
Subtask
Subtask
Subtask
Control
Task
Subtask
Subtask
Subtask
Close
Task
Subtask
Subtask
Subtask

## How to Use WBS Template
How to Use Our WBS Template
The following is a breakdown of the terms and sections in the task list and WBS template.
WBS Levels: These numbers represent the hierarchical relationship between project tasks and help group tasks that are part of a project phase.
Task Description: This section details what the deliverable is and also goes into the task and the subtasks necessary to complete it.
Task Owner: Every deliverable, task and subtask needs an owner to make sure the work is getting done, and that person is noted in this column.
Dependency: Some tasks cannot be started until the task before them has been completed, which means it’s dependent on that task and they should be linked. This is the space where you can note task dependencies.
Resources Needed: Whatever the task needs in terms of people, equipment, materials, etc., is listed here.
Task Status: This is where you can track the status of a specific task or subtask. The dropdown menu gives you the option of marking the task as unassigned, assigned, in progress, late or complete.
Cost: Note the financial commitment needed to get the deliverable done.
Start Date: When did work on the deliverable begin? Mark it here.
Estimated Completion: The estimated amount of time allotted for the completion of the deliverable should be noted here.
Finish Date: When the deliverable is done, note the end date here.
Using the Tree Diagram
On the second sheet there is a tree chart to visualize the work breakdown structure, from the highest level at the top to the lowest level at the bottom, where the bottom is more specific and the top more general. You don’t have to add all the extra data you filled into the previous sheet, just the deliverable, task and how every many subtasks are needed to get the work done.